## 17-239
Task Name | Estimate time( hour) | Take by | Actual Time | Status | Date Doing | Complete Process | Note
Requirement analyze | 10 | Lê Trần Mỹ Tâm |  | Done | 19/3/2025 | 12
[Report 1] Project Information | 2 | Lê Trần Mỹ Tâm |  | Done | 19/3/2025 | 2
[Report 1] Introduction | 2 | Lê Trần Mỹ Tâm |  | Done | 19/3/2025 | 2
[Report 1] Current Situation | 2 | Lê Trần Mỹ Tâm |  | Done | 19/3/2025 | 2
[Report 1] Problem Definition | 2 | Lê Trần Mỹ Tâm |  | Done | 19/3/2025 | 2
Draw ERD diagram | 8 | Nguyễn Thành Đạt |  | Done | 19/3/2025 | 8
Deploy database to SQL Sever (empty database) | 4 | Nguyễn Thành Đạt |  | Done | 19/3/2025 | 4
Learning how to use C# | 10 | Lê Trần Mỹ Tâm |  | Done | 19/3/2025 | 10
Total | 40 |  | 81.63% |  | Done task: | 105%
Requirement analyze | 12 | Nguyễn Thành Đạt |  | Done | 20/3/2025 | 12
[Report 1] Proposed Solution | 2 | Nguyễn Thành Đạt |  | Done | 20/3/2025 | 2
[Report 1] Functional Requirement | 5 | Nguyễn Thành Đạt |  | Done | 20/3/2025 | 5
[Report 1] Roles and Responsibility | 2 | Nguyễn Thành Đạt |  | Done | 20/3/2025 | 2
Create Use Case Spec | 10 | Nguyễn Thành Đạt |  | Done | 20/3/2025 | 10
Draw activity diagram | 10 | Nguyễn Thành Đạt |  | Done | 20/3/2025 | 10
Draw Sequence Diagram | 8 | Nguyễn Thành Đạt |  | Done | 20/3/2025 | 14
Draw Usecase Diagram | 8 | Hiệu Thị Sô Ny |  | Done | 20/3/2025 | 14
Total | 57 |  | 116.3% |  | Done task: | 121.1%
[UI Mockup Web] Login/Register Screen | 3 | Hiệu Thị Sô Ny |  | Done | 22/3/2025 | 3
[UI Mockup Web] Book information Screen | 4 | Hiệu Thị Sô Ny |  | Done | 22/3/2025 | 4
[UI Mockup Web] Customer Information Screen | 3 | Hiệu Thị Sô Ny |  | Done | 22/3/2025 | 3
[UI Mockup Web] Staff Information Screen | 4 | Hiệu Thị Sô Ny |  | Done | 22/3/2025 | 4
[UI Mockup Web] Update Book Screen | 5 | Hiệu Thị Sô Ny |  | Done | 22/3/2025 | 5
[UI Mockup Web] Payment Screen | 5 | Hiệu Thị Sô Ny |  | Done | 22/3/2025 | 5
[UI Mockup Web] Book List Screen | 5 | Hiệu Thị Sô Ny |  | Done | 23/3/2025 | 5
[UI Mockup Web] Search Book Screen | 5 | Hiệu Thị Sô Ny |  | Done | 23/3/2025 | 5
[Web] Admin's auction management screen | 5 | Hiệu Thị Sô Ny |  | Done | 23/3/2025 | 5
[Web] Admin's Customer management screen | 5 | Hiệu Thị Sô Ny |  | Done | 23/3/2025 | 5
[Web] Admin's Staff management screen | 5 | Hiệu Thị Sô Ny |  | Done | 23/3/2025 | 5
[Web] Admin's Report screen | 5 | Hiệu Thị Sô Ny |  | Done | 23/3/2025 | 5
GUI | 5 | Lê Trần Mỹ Tâm |  | Done | 23/3/2025 | 5
Draw State Diagram | 4 | Lê Trần Mỹ Tâm |  | Done | 23/3/2025 | 4
Requirement analyze | 8 | Hiệu Thị Sô Ny |  | Done | 23/3/2025 | 8
Total | 71 |  | 144.9% |  | Done task: | 88.73%
Requirement analyze | 9 | Nguyễn Ngọc Linh Nhi |  | Done | 24/3/2025 | 9
[UI Mockup Web] Login/Register Screen | 3 | Nguyễn Ngọc Linh Nhi |  | Done | 24/3/2025 | 3
[UI Mockup Web] Book information Screen | 3 | Nguyễn Ngọc Linh Nhi |  | Done | 24/3/2025 | 3
[UI Mockup Web] Customer Information Screen | 3 | Nguyễn Ngọc Linh Nhi |  | Done | 24/3/2025 | 3
[UI Mockup Web] Staff Information Screen | 3 | Nguyễn Ngọc Linh Nhi |  | Done | 24/3/2025 | 3
[UI Mockup Web] Update Book Screen | 4 | Nguyễn Ngọc Linh Nhi |  | Done | 24/3/2025 | 4
[UI Mockup Web] Payment Screen | 2 | Nguyễn Ngọc Linh Nhi |  | Done | 24/3/2025 | 2
[UI Mockup Web] Book List Screen | 3 | Nguyễn Ngọc Linh Nhi |  | Done | 24/3/2025 | 3
[UI Mockup Web] Search Book Screen | 2 | Nguyễn Ngọc Linh Nhi |  | Done | 24/3/2025 | 2
[Web] Admin's auction management screen | 3 | Nguyễn Ngọc Linh Nhi |  | Done | 24/3/2025 | 3
[Web] Admin's Customer management screen | 4 | Nguyễn Ngọc Linh Nhi |  | Done | 24/3/2025 | 3
[Web] Admin's Staff management screen | 5 | Nguyễn Ngọc Linh Nhi |  | Done | 24/3/2025 | 5
[Web] Admin's Report screen | 5 | Nguyễn Ngọc Linh Nhi |  | Done | 24/3/2025 | 5
Deploy database to SQL Sever (empty database) | 3 | Hiệu Thị Sô Ny |  | Done | 24/3/2025 | 2
Interface Design | 3 | Nguyễn Ngọc Linh Nhi |  | Done | 24/3/2025 | 3
[Implement UI] Login/Register Screen | 4 | Nguyễn Ngọc Linh Nhi |  | Done | 24/3/2025 | 2
[Implement UI] Database Screen | 4 | Nguyễn Ngọc Linh Nhi |  | Done | 24/3/2025 | 4
[Implement UI] Entertainment Screen | 4 | Nguyễn Ngọc Linh Nhi |  | Done | 24/3/2025 | 4
Draw activity diagram | 3 | Nguyễn Ngọc Linh Nhi |  | Done | 24/3/2025 | 5
Total | 61 |  | 124.5% |  | Done task: | 96.72%